03/18/2024 Meeting Minutes		5:00 PM – 7:00 PM

** THIS MEETING WAS CANCELLED AND SUBSTITUED VIA CHAT LOGS. VIEW AT END OF DOCUMENT **

Attendees:

Molly Atkinson, Dorothy McChesney, Danielle Robinson

Outline of Meeting

Preview upcoming work

Discussed completed work and shared what was completed

Project Scope

Mission Statement

Assigned to: Dorothy

Due: 3/6 11:59 PM

Project Goals

Assigned to: Danielle

Requires: Mission Statement

Due: 3/11 11:59 PM

Objective Statements

Assigned to: Molly

Requires: Project Goals

Due: 3/12 11:59 PM

--------------------------------

Schedule Overview

Detailed Schedule as an Appendix Item

Assigned to: Danielle

Due: 3/15 11:59 PM

Budget Overview

Detailed Budget as an Appendix Item

Assigned to: Molly

Requires: Schedule

Due: 3/18 11:59 PM

Details and Assumptions

Assigned to: Dot

Due: 3/15 11:59 PM

--------------------------------

Contract Components

Invoicing

Assigned to: Danielle

Due: 3/22 11:59	PM

WBS as an Appendix Item

Assigned to: Dot

Due: 3/22 11:59 PM

Creative Brief as an Appendix Item

Assigned to: Team/copy paste

Due: 3/4 7:00 PM

Client Documents

Approval Form

Blank & Completed

Assigned to: Molly

Due: 3/8 11:59 PM

Change Order Form

Blank & Completed

Assigned to: Dot

Due: 3/11 11:59 PM

Management Documents

Blank and Filled Out Budgeting

Assigned to: Molly

Requires: Budget Overview

Due: 3/19 11:59 PM

Web Server

Upload new documents to web server

Assigned to: Dorothy

Due: 3/26 11:59 PM

Chat Log