03/04/2024 Meeting Minutes		5:30 PM – 7:30 PM

Attendees:

Molly Atkinson, Dorothy McChesney, Danielle Robinson

Outline of Meeting

Address team needs

Turn in previous week’s work

Peer Review

Creative Brief

Preview upcoming work

Discussed work and divided evenly, assigned internal due dates (see below)

Project Scope

Mission Statement

Assigned to: Dorothy

Due: 3/6 11:59 PM

Project Goals

Assigned to: Danielle

Requires: Mission Statement

Due: 3/11 11:59 PM

Objective Statements

Assigned to: Molly

Requires: Project Goals

Due: 3/12 11:59 PM

--------------------------------

Schedule Overview

Detailed Schedule as an Appendix Item

Assigned to: Danielle

Due: 3/15 11:59 PM

Budget Overview

Detailed Budget as an Appendix Item

Assigned to: Molly

Requires: Schedule

Due: 3/18 11:59 PM

Details and Assumptions

Assigned to: Dot

Due: 3/15 11:59 PM

--------------------------------

Contract Components

Invoicing

Assigned to: Danielle

Due: 3/22 11:59	PM

WBS as an Appendix Item

Assigned to: Dot

Due: 3/22 11:59 PM

Creative Brief as an Appendix Item

Assigned to: Team/copy paste

Due: 3/4 7:00 PM

Client Documents

Approval Form

Blank & Completed

Assigned to: Molly

Due: 3/8 11:59 PM

Change Order Form

Blank & Completed

Assigned to: Dot

Due: 3/11 11:59 PM

Management Documents

Blank and Filled Out Budgeting

Assigned to: Molly

Due: 3/19 11:59 PM

Web Server

Upload new documents to web server

Assigned to: Dorothy

Due: 3/26 11:59 PM