## Content Audit
Client: RedBovineDairy.com Red Bovine Dairy
Website Audit
ITEM | Description | Action | Importance 1 least- 5 most
UX (User Experience) | Templates layout, readability, and visual appeal | Update to embrace a modernistic design while holding onto the authenticity and natural charm their current site has, resulting in a more efficient, easy-to-navigate site with a fresh look. | 5
SEO Best Practices | - Are keywords effectively incorporated into the content? - Is the content optimized for search engines? | Keep but update the keywords and tags to include the events | 4
Responsiveness | Template is tested on varius devices to ensure its responsiveness | Update template to make it more user friendly for smaller screens such as iphone or iPad mini | 5
Accessibility | Does the template comply with accessibility standards? | Update alt texts and color usage | 5
Consistency | is it accurate and organized? | keep but fix the positioning | 3
Content Relevance | - Is the content aligned with the website's goals and objectives? - Is it still relevant to the target audience? | Keep | 3
Calls to Action | - Are there clear CTAs prompting users to take action? - Do they stand out and encourage engagement? | Update the CTA to the new layout and color scheme. | 4
Performance | - Does the content load quickly? - Are there any issues with broken links or missing media files? | Update links and optimize the site after each upload | 3
Legal Compliance | Ensure the template complies with relevant laws and regulations (e.g., GDPR, CCPA) regarding data privacy and user consent. | Update when a update to laws and regulations are live | 5
Feedback Mechanism | Check if the template includes a way for users to provide feedback or contact you for further information. | Keep the contact page free from clutter | 4
Content Management System | Ensure the template is compatible with your CMS and allows for easy content updates and management. | Refresh the CMS with updated material for upcoming content | 5

## Content Delivery Plan
Main Pages | [6 empty] | Sub Pages
Class number | Content Name | HTML Page | Status | Assigned | Draft Due | Final Due | Class number | Content Name | HTML Page | Status | Assigned | Draft Due | Final Due
0 | Home | index.htm | Not Started | Dorothy | 2024-04-18 | 2024-04-19 | 2.2.1 | Milking Tours | milking_tour.htm | Not Started | Molly | 2024-04-24 | 2024-04-26
1.1 | History | history.htm | Not Started | Danielle | 2024-04-18 | 2024-04-19 | 2.2.2 | Cheese Tours | cheese_tour.htm | Not Started | Molly | 2024-04-24 | 2024-04-26
1.2 | Location | location.htm | Not Started | Molly | 2024-04-18 | 2024-04-19 | 2.2.3 | Ice Cream Tours | ice_cream_tour.htm | Not Started | Molly | 2024-04-24 | 2024-04-26
1.3 | Social Media | social.htm | Not Started | Danielle | 2024-04-18 | 2024-04-19 | 2.3.1 | Baby Animal Photo Ops | babies.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26
1.4 | News | news.htm | Not Started | Molly | 2024-04-18 | 2024-04-19 | 2.3.2 | Tulips and Bouquets | tulips.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26
2 | Events | events.htm | Not Started | Dorothy | 2024-04-18 | 2024-04-19 | 2.3.3 | Breakfast on the Farm | breakfast.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26
2.1 | 100-Year Celebration | 100_year.htm | Not Started | Danielle | 2024-04-24 | 2024-04-26 | 2.4.1 | Picnic On The Farm | picnic.htm | Not Started | Danielle | 2024-04-24 | 2024-04-26
2.2 | Farm Visits | visits.htm | Not Started | Molly | 2024-04-24 | 2024-04-26 | 2.4.2 | Butterfly Garden | butterflies.htm | Not Started | Danielle | 2024-04-24 | 2024-04-26
2.3 | Spring Celebration | spring.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26 | 2.4.3 | Horse-riding and Bonfire | bonfire.htm | Not Started | Danielle | 2024-04-24 | 2024-04-26
2.4 | Summer Swing | summer.htm | Not Started | Danielle | 2024-04-24 | 2024-04-26 | 2.5.1 | Farm to Table Dinner | dinner.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26
2.5 | Fall Festival | fall.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26 | 2.5.2 | Pumpkin Patch Hayride | hayride.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26
3 | Products | products.htm | Not Started | Molly | 2024-05-01 | 2024-05-03 | 2.5.3 | Apple Picking | apples.htm | Not Started | Dorothy | 2024-04-24 | 2024-04-26
3.1 | Milk | milk.htm | Not Started | Molly | 2024-05-01 | 2024-05-03
3.2 | Cheese | cheese.htm | Not Started | Molly | 2024-05-01 | 2024-05-03
3.3 | Ice Cream | ice_cream.htm | Not Started | Danielle | 2024-05-01 | 2024-05-03
3.4 | Other | other.htm | Not Started | Danielle | 2024-05-01 | 2024-05-03
4 | Services | services.htm | Not Started | Dorothy | 2024-05-01 | 2024-05-03
4.1 | Boarding | boarding.htm | Not Started | Dorothy | 2024-05-01 | 2024-05-03
4.2 | Victory Gardens | gardens.htm | Not Started | Dorothy | 2024-05-01 | 2024-05-03
5 | Learning | learning.htm | Not Started | Danielle | 2024-05-08 | 2024-05-10
5.1 | Becoming a Farmer | farmer.htm | Not Started | Danielle | 2024-05-08 | 2024-05-10
5.2 | Hobby Farm 101 | hobby_farm.htm | Not Started | Dorothy | 2024-05-08 | 2024-05-10
5.3 | Farming Professions | professions.htm | Not Started | Dorothy | 2024-05-08 | 2024-05-10
5.4 | Farm Safety | safety.htm | Not Started | Molly | 2024-05-08 | 2024-05-10
5.5 | Organic Farming | organic_farming.htm | Not Started | Molly | 2024-05-08 | 2024-05-10
6 | Careers | careers.htm | Not Started | Dorothy | 2024-05-15 | 2024-05-20
6.1 | Farming Careers | careers_in_farming.htm | Not Started | Dorothy | 2024-05-15 | 2024-05-20
6.2 | Open Positions | job_oppurtunities.htm | Not Started | Dorothy | 2024-05-15 | 2024-05-20
7 | Gallery | gallery.htm | Not Started | Dorothy | 2024-05-15 | 2024-05-20
8 | Contact | contact.htm | Not Started | Molly | 2024-05-15 | 2024-05-20

## Copy of In Depth Schedule
Task | Work Days | Date Started: Wed 3/13/24 | Final Day: Tue 6/18/24 | Role
Define the project | 9 days | 2024-03-13 | 2024-03-25 | N/A
Client Survey | 2 days | 2024-03-14 | 2024-03-19 | N/A
Develop Project Analysis and Plan | 4 Days | 2024-03-14 | 2024-03-19 | N/A
Competitive Analysis Report | 1 1/2 Days | 2024-03-14 | 2024-03-15 | Project Manager
Audience Analysis Report | 1 Day | 2024-03-15 | 2024-03-18 | Project Manager
Creative Brief | 1 Day | 2024-03-18 | 2024-03-19 | Project Manager
Develop Project Plan | 1 day | 2024-03-19 | 2024-03-20 | Project Manager
Set Budget and Create Schedules | 2 days | 2024-03-20 | 2024-03-21 | Project Manager
Create Scope | 2 days | 2024-03-21 | 2024-03-22 | Project Manager
Develop Site Structure | 3.5 days | 2024-03-26 | 2024-03-29 | N/A
Conduct Planning Workshop | 1 dat | 2024-03-26 | 2024-03-29 | Project Manager
Site Outline and Sitemapping | 1 day | 2024-03-27 | 2024-02-27 | Creative Lead
Production Lead
Naming Conventions and Labeling | 1/2 day | 2024-03-28 | 2024-03-28 | Creative Lead
Project Manager
Wireframing and Navigation | 1 day | 2024-03-28 | 2024-03-29 | Creative Lead
Production Lead
Design Visual Interface | 10 days | 2024-04-01 | 2024-04-12 | N/A
Create Design and Concepts | 8 days | 2024-04-01 | 2024-04-10
Colors and Layouts | 4 days | 2024-04-01 | 2024-04-04 | Creative Lead
Production Lead
Typography and Graphics | 4 days | 2024-04-03 | 2024-04-08 | Creative Lead
Production Lead
Test for Functionality | 5 days | 2024-04-08 | 2024-04-12 | Creative Lead
Production Lead
Build and Integrate | 26 days | 2024-04-15 | 2024-05-20 | N/A
Content and File Structure | 20 days | 2024-04-15 | 2024-05-10
Create HTML/CSS Templates and Pages | 8 days | 2024-04-15 | 2024-04-25 | Creative Lead
Production Lead
Testing Functionality | 4 days | 2024-04-24 | 2024-04-29 | Creative Lead
Project Manager
Quality Assurance Manager
Production Lead
Optimization and Bug Fixes | 5 days | 2024-04-26 | 2024-05-06 | Creative Lead
Production Lead
Quality Assurance | 5 days | 2024-04-26 | 2024-05-06 | Quality Assurance Manager
Validation and Final Check | 6 days | 2024-05-13 | 2024-05-20 | Creative Lead
Quality Assurance Manager
Production Lead
Project Manager
Delivery and Launch | 9 days | 2024-05-21 | 2024-05-31 | N/A
Handoff and Launch | 2 days | 2024-05-24 | 2024-05-27
Create Handoff Packet | 1 day | 2024-05-24 | 2024-05-24 | Project Manager
Site Launch | 1 day | 2024-05-27 | 2024-05-27 | Project Manager
Maintenance | 10 days | 2024-05-31 | 2024-06-13 | N/A
Develop Maintenance Training | 3 days | 2024-06-05 | 2024-06-07 | Creative Lead
Production Lead
Maintenance Training | 4 days | 2024-06-10 | 2024-06-13 | Creative Lead
Production Lead
Contract Closure | 3 days | 2024-06-14 | 2024-06-18 | N/A
Measure Success/Complete Notes | 1 day | 2024-06-17 | 2024-06-17 | Project Manager
Close Contract | 1 day | 2024-06-18 | 2024-06-18 | Project Manager